## Executive Roadmap
Sprint | Theme | Objective | Workstream | Start | End | Status | Story Points | Story Count | Exit Gate
S0 | Architecture Baseline | Freeze scope, risks, contracts and environments | Architecture | 2026-10-12 | 2026-10-23 | Planned | 0 | 0 | Architecture, threat model and backlog approved
S1 | Contracts and Identity | Schemas, signing identities and IPC skeleton | Platform | 2026-10-26 | 2026-11-06 | Planned | 0 | 0 | Integrated increment demonstrated
S2 | Policy Core | OPA, immutable policy, risk and tests | Security | 2026-11-09 | 2026-11-20 | Planned | 0 | 0 | Integrated increment demonstrated
S3 | Approval and Evidence | Trusted approval, stop, audit and telemetry | Security | 2026-11-23 | 2026-12-04 | Planned | 0 | 0 | No action can bypass policy, approval or audit
S4 | Cognitive Runtime | LangGraph, model gateway and checkpoints | Agent | 2026-12-07 | 2026-12-18 | Planned | 0 | 0 | Integrated increment demonstrated
S5 | Safe Windows Broker | App/window/media capabilities and leases | Windows | 2026-12-21 | 2027-01-01 | Planned | 0 | 0 | Integrated increment demonstrated
S6 | Verification and Recovery | Evidence, idempotency and uncertainty | Reliability | 2027-01-04 | 2027-01-15 | Planned | 0 | 0 | Verified/failed/uncertain behavior proven
S7 | Privacy and Perception | UIA, exclusions, labels and redaction | Privacy | 2027-01-18 | 2027-01-29 | Planned | 0 | 0 | Integrated increment demonstrated
S8 | Tool Platform Core | Catalog, retrieval, grants and runtime | Tools | 2027-02-01 | 2027-02-12 | Planned | 0 | 0 | Integrated increment demonstrated
S9 | Initial MCP Pack | Restricted browser/file/git/document/search tools | Tools | 2027-02-15 | 2027-02-26 | Planned | 0 | 0 | Initial MCP pack isolated and contract-pinned
S10 | Voice | Wake, VAD, STT, TTS and interruption | Interaction | 2027-03-01 | 2027-03-12 | Planned | 0 | 0 | Integrated increment demonstrated
S11 | 3D Character | Asset MVP, Godot overlay and animation states | Character | 2027-03-15 | 2027-03-26 | Planned | 0 | 0 | Voice and character usable as one experience
S12 | Controlled Memory | Admission, retrieval, provenance and deletion | Memory | 2027-03-29 | 2027-04-09 | Planned | 0 | 0 | Integrated increment demonstrated
S13 | Integrated Workflows | Research, documents and development reads | Product | 2027-04-12 | 2027-04-23 | Planned | 0 | 0 | Integrated increment demonstrated
S14 | Supervised Desktop | UIA interaction and workflow drafts | Windows | 2027-04-26 | 2027-05-07 | Planned | 0 | 0 | Supervised desktop actions stop safely on ambiguity
S15 | Constrained Proactivity | Triggers, budgets, reasons and quiet hours | Agent | 2027-05-10 | 2027-05-21 | Planned | 0 | 0 | Integrated increment demonstrated
S16 | Hardening | Security, privacy, reliability and performance | Quality | 2027-05-24 | 2027-06-04 | Planned | 0 | 0 | Adversarial and privacy release thresholds met
S17 | Beta and Release | Installer, pilot, documentation and gates | Release | 2027-06-07 | 2027-06-18 | Planned | 0 | 0 | Production readiness review approves beta release

## Sprint Backlog
Story ID | Story | Sprint | Sprint Theme | Workstream | Owner Role | Priority | Points | Dependencies | Acceptance Criterion | Status
ARCH-001 | Approve architecture decision record set | S0 | Architecture Baseline | Architecture | Lead Architect | Must | 5 | None | Architecture v1 signed off | Planned
SEC-001 | Create threat model and trust-boundary data-flow diagrams | S0 | Architecture Baseline | Security | Security Engineer | Must | 8 | None | Threats mapped to controls | Planned
PLAT-001 | Create monorepo, CI quality gates and environments | S0 | Architecture Baseline | Platform | Platform Engineer | Must | 8 | None | Clean build/test pipeline | Planned
UX-001 | Convert character references into production asset brief | S0 | Architecture Baseline | Character | 3D/UX Artist | Must | 5 | None | Brief covers rig, LOD and accessories | Planned
PM-001 | Baseline outcomes, scope, risks and sprint governance | S0 | Architecture Baseline | Program | Product Owner | Must | 3 | None | Backlog and gates approved | Planned
CON-001 | Define Task, ActionIntent and expected-effect schemas | S1 | Contracts and Identity | Contracts | Platform Engineer | Must | 8 | S0 | Schemas validated with examples | Planned
CON-002 | Define policy decision, approval and capability grant schemas | S1 | Contracts and Identity | Contracts | Security Engineer | Must | 8 | S0 | Signature fields and expiry specified | Planned
CON-003 | Define normalized result, evidence and audit schemas | S1 | Contracts and Identity | Contracts | Reliability Engineer | Must | 5 | S0 | Versioned compatibility tests pass | Planned
IPC-001 | Prototype ACL-protected named-pipe service identity | S1 | Contracts and Identity | Platform | Windows Engineer | Must | 8 | S0 | Unauthorized clients rejected | Planned
POL-001 | Deploy local OPA service and signed policy bundles | S2 | Policy Core | Security | Security Engineer | Must | 8 | S1 | Bundle signature/version enforced | Planned
POL-002 | Implement R0–R4 deterministic risk classifier | S2 | Policy Core | Security | Security Engineer | Must | 8 | S1 | Risk matrix tests pass | Planned
POL-003 | Implement immutable root restrictions | S2 | Policy Core | Security | Windows Engineer | Must | 8 | S1 | Conversation cannot modify restrictions | Planned
POL-004 | Build policy decision test harness | S2 | Policy Core | Quality | QA/Security Engineer | Must | 5 | S1 | Allow/deny/ask matrix automated | Planned
APR-001 | Build technically separate trusted approval UI | S3 | Approval and Evidence | Security UX | Windows Engineer | Must | 13 | S2 | Exact preview and expiry work | Planned
SAFE-001 | Implement global emergency stop and tray pause | S3 | Approval and Evidence | Safety | Windows Engineer | Must | 8 | S2 | Actuation revokes within objective | Planned
AUD-001 | Implement append-only hash-chained audit writer | S3 | Approval and Evidence | Audit | Platform Engineer | Must | 8 | S2 | Tamper checks and recovery pass | Planned
OTEL-001 | Deploy OTel Collector and baseline trace correlation | S3 | Approval and Evidence | Observability | SRE | Must | 8 | S2 | Trace/task IDs visible end-to-end | Planned
AGT-001 | Implement LangGraph task state and deterministic gates | S4 | Cognitive Runtime | Agent | AI Engineer | Must | 13 | S3 | Graph pauses/resumes at approval | Planned
AGT-002 | Add durable checkpoints and idempotency references | S4 | Cognitive Runtime | Reliability | AI Engineer | Must | 8 | S3 | Crash test does not duplicate work | Planned
LLM-001 | Implement provider-neutral endpoint profiles | S4 | Cognitive Runtime | LLM | AI Engineer | Must | 8 | S3 | Provider swap requires configuration only | Planned
LLM-002 | Enforce structured outputs, budgets and circuit breakers | S4 | Cognitive Runtime | LLM | Platform Engineer | Must | 8 | S3 | Malformed/budget tests stop safely | Planned
WIN-001 | Create signed standard-user C# Windows broker | S5 | Safe Windows Broker | Windows | Windows Engineer | Must | 13 | S4 | Only declared capabilities exposed | Planned
WIN-002 | Implement allowlisted application launch/focus | S5 | Safe Windows Broker | Windows | Windows Engineer | Must | 8 | S4 | Publisher/path verified | Planned
WIN-003 | Implement safe window, volume and media operations | S5 | Safe Windows Broker | Windows | Windows Engineer | Must | 8 | S4 | State verified after operations | Planned
WIN-004 | Implement single desktop lease and human takeover | S5 | Safe Windows Broker | Safety | Windows Engineer | Must | 8 | S4 | Mouse/keyboard activity revokes lease | Planned
VER-001 | Build independent verifier service and predicate API | S6 | Verification and Recovery | Reliability | Reliability Engineer | Must | 13 | S5 | Three-state outcomes supported | Planned
VER-002 | Implement process/window/file verification adapters | S6 | Verification and Recovery | Reliability | Windows Engineer | Must | 8 | S5 | Evidence independent of executor | Planned
REL-001 | Implement idempotency registry and bounded retries | S6 | Verification and Recovery | Reliability | Platform Engineer | Must | 8 | S5 | Replay suite has zero duplicate effects | Planned
REL-002 | Implement compensation and UNCERTAIN workflow | S6 | Verification and Recovery | Reliability | AI Engineer | Must | 5 | S5 | Non-idempotent uncertainty never retries | Planned
PRV-001 | Implement source-based privacy classification | S7 | Privacy and Perception | Privacy | Privacy Engineer | Must | 8 | S6 | Source policy overrides detector | Planned
PRV-002 | Implement app/site/folder/region exclusions | S7 | Privacy and Perception | Privacy | Windows Engineer | Must | 13 | S6 | Excluded context never captured | Planned
PRV-003 | Integrate local redaction and Presidio patterns | S7 | Privacy and Perception | Privacy | Privacy Engineer | Must | 8 | S6 | Release-view tests pass | Planned
PER-001 | Implement metadata and UIA perception ladder | S7 | Privacy and Perception | Perception | Windows Engineer | Must | 13 | S6 | Screenshots used only when required | Planned
PRV-004 | Implement private-mode indicators and short-lived buffers | S7 | Privacy and Perception | Privacy UX | Interaction Engineer | Must | 5 | S6 | State is always visible | Planned
TOOL-001 | Implement trusted catalog and signed tool contracts | S8 | Tool Platform Core | Tools | Platform Engineer | Must | 13 | S7 | Contract drift quarantines tool | Planned
TOOL-002 | Implement hybrid retrieval and policy pre-filter | S8 | Tool Platform Core | Tools | AI Engineer | Must | 8 | S7 | Top-k evaluation meets threshold | Planned
TOOL-003 | Implement capability validation and secret brokering | S8 | Tool Platform Core | Tools | Security Engineer | Must | 13 | S7 | Secrets absent from prompts/logs | Planned
TOOL-004 | Implement result normalizer and runtime supervisor | S8 | Tool Platform Core | Tools | Platform Engineer | Must | 13 | S7 | Timeout/cancel/output limits pass | Planned
TOOL-005 | Prototype ToolHive isolation on target Windows setup | S8 | Tool Platform Core | Tools | SRE | Must | 8 | S7 | Mount and egress tests pass | Planned
MCP-001 | Onboard Playwright MCP in isolated profile | S9 | Initial MCP Pack | Tools | Tool Engineer | Must | 8 | S8 | Domain/download restrictions pass | Planned
MCP-002 | Wrap Filesystem and Git MCP read-only | S9 | Initial MCP Pack | Tools | Tool Engineer | Must | 13 | S8 | Root/junction/write tests pass | Planned
MCP-003 | Onboard MarkItDown with sandboxed local parsing | S9 | Initial MCP Pack | Tools | Tool Engineer | Must | 8 | S8 | Malicious/large documents bounded | Planned
MCP-004 | Onboard Brave Search and Time MCP | S9 | Initial MCP Pack | Tools | Tool Engineer | Must | 5 | S8 | Queries redacted; output tainted | Planned
MCP-005 | Integrate MCP Inspector and scanning pipeline | S9 | Initial MCP Pack | Security | Security Engineer | Must | 8 | S8 | Promotion requires scan record | Planned
VOX-001 | Select and integrate wake word, VAD and streaming STT | S10 | Voice | Voice | Interaction Engineer | Must | 13 | S9 | Latency/false-wake baseline met | Planned
VOX-002 | Integrate streaming TTS and lip-sync events | S10 | Voice | Voice | Interaction Engineer | Must | 8 | S9 | First audio latency measured | Planned
VOX-003 | Implement echo cancellation and barge-in | S10 | Voice | Voice | Interaction Engineer | Must | 13 | S9 | User interruption works reliably | Planned
VOX-004 | Add push-to-talk, sleep and privacy controls | S10 | Voice | Voice | UX Engineer | Must | 5 | S9 | Controls accessible and audited | Planned
CHR-001 | Create rigged 3D character MVP from references | S11 | 3D Character | Character | 3D Artist | Must | 13 | S10 | Recognizable front/side/back asset | Planned
CHR-002 | Build Godot transparent click-through overlay | S11 | 3D Character | Character | Godot Engineer | Must | 13 | S10 | DPI/multi-monitor tests pass | Planned
CHR-003 | Implement semantic animation state machine | S11 | 3D Character | Character | Godot Engineer | Must | 8 | S10 | All Jarvis states visible | Planned
CHR-004 | Add locomotion, facial and accessory animation | S11 | 3D Character | Character | 3D/Animation Artist | Must | 13 | S10 | Transitions stable at taskbar scale | Planned
MEM-001 | Implement memory classes and provenance schema | S12 | Controlled Memory | Memory | Data Engineer | Must | 8 | S11 | Every item has source/labels/expiry | Planned
MEM-002 | Implement admission, contradiction and dedupe logic | S12 | Controlled Memory | Memory | AI Engineer | Must | 13 | S11 | Poisoning suite blocks instructions | Planned
MEM-003 | Implement hybrid retrieval with permission filter | S12 | Controlled Memory | Memory | AI Engineer | Must | 8 | S11 | Forbidden items never retrieve | Planned
MEM-004 | Build inspect/edit/delete memory dashboard | S12 | Controlled Memory | Memory UX | Frontend Engineer | Must | 13 | S11 | Deletion propagates to vectors/cache | Planned
WF-001 | Ship cited public research workflow | S13 | Integrated Workflows | Product | AI/Tool Engineer | Must | 8 | S12 | Claims preserve provenance | Planned
WF-002 | Ship local document understanding workflow | S13 | Integrated Workflows | Product | AI/Tool Engineer | Must | 8 | S12 | Private docs stay within policy | Planned
WF-003 | Ship read-only repository analysis workflow | S13 | Integrated Workflows | Product | AI/Tool Engineer | Must | 8 | S12 | No mutation capability available | Planned
WF-004 | Build tool composition and parallel-read scheduler | S13 | Integrated Workflows | Tools | Platform Engineer | Must | 13 | S12 | DAG conflicts serialize correctly | Planned
UIA-001 | Implement UIA candidate retrieval and confidence scoring | S14 | Supervised Desktop | Windows | Windows Engineer | Must | 13 | S13 | Ambiguity causes stop/ask | Planned
UIA-002 | Implement fresh-target check and semantic invocation | S14 | Supervised Desktop | Windows | Windows Engineer | Must | 13 | S13 | Stale target test cannot execute | Planned
WF-005 | Implement shadow-mode workflow demonstration capture | S14 | Supervised Desktop | Learning | AI Engineer | Must | 8 | S13 | Draft skills cannot self-promote | Planned
UX-002 | Build supervised execution timeline | S14 | Supervised Desktop | Product UX | Frontend Engineer | Must | 8 | S13 | User sees each pending/result step | Planned
PRO-001 | Implement deterministic trigger service | S15 | Constrained Proactivity | Proactivity | Platform Engineer | Must | 8 | S14 | Only registered triggers fire | Planned
PRO-002 | Implement relevance, quiet-hours and cooldown engine | S15 | Constrained Proactivity | Proactivity | AI Engineer | Must | 8 | S14 | Frequency budgets enforced | Planned
PRO-003 | Add visible reason and per-rule controls | S15 | Constrained Proactivity | Proactivity UX | Frontend Engineer | Must | 5 | S14 | Every interruption is explainable | Planned
PRO-004 | Integrate initial calendar/build/battery triggers | S15 | Constrained Proactivity | Proactivity | Tool Engineer | Must | 8 | S14 | No consequential bypass | Planned
RED-001 | Run prompt-injection and confused-deputy campaign | S16 | Hardening | Security | Red Team | Must | 13 | S15 | Critical scenarios blocked | Planned
RED-002 | Run MCP supply-chain and sandbox escape tests | S16 | Hardening | Security | Red Team | Must | 13 | S15 | No host-boundary escape | Planned
QA-001 | Run privacy leakage and memory poisoning suite | S16 | Hardening | Quality | QA/Privacy Engineer | Must | 13 | S15 | Release thresholds met | Planned
PERF-001 | Optimize voice, graph, policy and character latency | S16 | Hardening | Performance | Performance Engineer | Must | 8 | S15 | Latency budgets met | Planned
DR-001 | Test backup, restore, crash and update rollback | S16 | Hardening | Reliability | SRE | Must | 8 | S15 | Recovery runbook passes | Planned
REL-003 | Create signed installer and rollback-capable updater | S17 | Beta and Release | Release | Release Engineer | Must | 13 | S16 | Signature/update rollback verified | Planned
OPS-001 | Finalize Grafana action-review and operations dashboards | S17 | Beta and Release | Operations | SRE | Must | 8 | S16 | User can trace complete action | Planned
DOC-001 | Complete user, administrator and incident documentation | S17 | Beta and Release | Documentation | Technical Writer | Must | 8 | S16 | Docs pass operational walkthrough | Planned
BETA-001 | Run controlled pilot and resolve release blockers | S17 | Beta and Release | Release | Product/QA | Must | 13 | S16 | Pilot acceptance gates pass | Planned
GATE-001 | Conduct production readiness review | S17 | Beta and Release | Governance | Architecture Board | Must | 5 | S16 | Go/no-go decision recorded | Planned

## Architecture Workstreams
Workstream | Primary Deliverables | Key Interfaces | Primary Owner | Quality Evidence | Target Sprints
Experience/Character | 3D asset, Godot overlay, semantic animation and status UI | Interaction events; trusted UI separation | Godot + 3D Team | DPI, multi-monitor, frame time and accessibility tests | S0, S10–S11
Interaction | Wake/VAD/STT/TTS, barge-in and privacy controls | Orchestrator and character cues | Interaction Engineer | False-wake, latency and interruption metrics | S10–S11
Agent Orchestration | LangGraph graphs, planning, checkpoints and recovery | LLM gateway, policy and tool platform | AI Engineer | Bounded loop and crash/replay tests | S4 onward
Policy/Guardrails | OPA, PEP/PIP, risk, approvals and grants | All effectful paths | Security Engineer | Policy matrix and adversarial suite | S1–S3, S16
Windows | Signed brokers, UIA, process containment and leases | Policy grants and verifier | Windows Engineer | Publisher/target/takeover tests | S5–S7, S14
Tool Platform | Registry, retrieval, contracts, isolation and MCP portfolio | LangGraph, OPA and verifier | Platform/Tool Engineer | Contract drift and sandbox tests | S8–S9, S13
Privacy | Exclusions, labels, redaction and release policy | Sensors, LLM, memory and telemetry | Privacy Engineer | Leakage and excluded-app tests | S7, S12, S16
Verification | Predicates, evidence, idempotency and uncertainty | Every effectful capability | Reliability Engineer | No duplicate effects; evidence coverage | S6 onward
Memory | Classes, admission, retrieval, provenance and deletion | Orchestrator and privacy | Data/AI Engineer | Poisoning and deletion tests | S12
Observability/Audit | OTel stack, action review and hash-chained journal | All components | SRE | Trace completeness and tamper checks | S3 onward

## Risk Register
Risk ID | Risk | Probability | Impact | Rating | Mitigation | Trigger/Indicator | Owner | Review Sprint | Status
R-01 | Indirect prompt injection causes tool misuse | High | Critical | Critical | Data/instruction separation, taint, OPA, destination checks and adversarial tests | Observed content attempts to alter goal/authority | Security Engineer | Every sprint | Open
R-02 | MCP supply-chain compromise | Medium | Critical | High | Pin digests, SBOM/scan, isolation, egress/mount controls and quarantine | Schema/digest/dependency changes | Tool Platform Lead | S8–S16 | Open
R-03 | Private context reaches remote endpoint or telemetry | Medium | Critical | High | Local source policy, release views, secret tests and telemetry allowlists | Secret canary appears outside privacy boundary | Privacy Engineer | S7–S16 | Open
R-04 | UI automation targets wrong window or element | High | High | High | Publisher identity, fresh UIA snapshot, confidence margin and verification | Focus/layout/DPI change between plan and action | Windows Engineer | S5–S16 | Open
R-05 | Retry duplicates external effect | Medium | Critical | High | Idempotency registry, prepare/commit and stop on uncertainty | Timeout after effect with missing response | Reliability Engineer | S6 onward | Open
R-06 | User mistakes character prompt for trusted approval | Medium | High | High | Separate signed native approval UI and consistent trusted visual language | Approval shown inside avatar/website | Security UX | S3 onward | Open
R-07 | Character asset/overlay misses performance target | Medium | Medium | Medium | LOD, bounded physics, early Godot spike and frame-time budget | High GPU/CPU or input interference | Godot Lead | S0, S11 | Open
R-08 | Voice latency or false wakes harm trust | Medium | Medium | Medium | Local VAD/wake, model benchmarks, push-to-talk and latency telemetry | False wake/response latency exceeds threshold | Interaction Lead | S10 | Open
R-09 | Memory stores false or poisoned instructions | Medium | High | High | Quarantine, provenance, contradiction checks and no executable remembered text | Untrusted claim retrieved as workflow | Memory Lead | S12–S16 | Open
R-10 | Tool breadth creates unreliable selection | High | Medium | High | Progressive retrieval, initial 10–15 tools and selection evaluation | Incorrect-tool/policy-denial rate rises | AI/Tool Lead | S8 onward | Open
R-11 | Target hardware cannot run full local stack | Medium | Medium | Medium | Baseline target hardware; configurable services; performance spike | Sustained resource budget breach | SRE | S0, S10–S16 | Open
R-12 | Audit/trace storage leaks content or grows unbounded | Medium | High | High | Field allowlists, retention tiers, quotas, encryption and review | Unexpected content/cardinality/storage growth | SRE/Privacy | S3 onward | Open

## Acceptance Gates
Gate | Target Sprint | Required Evidence | Pass Condition | Owner | Status
G0 Architecture | S0 | ADRs, scope, threat model, data flow and backlog | Architecture board approves baseline | Lead Architect | Planned
G1 Control Plane | S3 | Policy tests, approval signatures, emergency stop and audit chain | No tested effect path bypasses controls | Security Lead | Planned
G2 Safe Actuation | S6 | Broker/lease, idempotency and independent verification suite | Zero duplicate effects; uncertainty stops | Reliability Lead | Planned
G3 Privacy | S7 | Excluded-app, release-view, private-mode and telemetry leak tests | Prohibited data does not cross boundary | Privacy Lead | Planned
G4 Tool Platform | S9 | Pinned contracts, isolation, egress/mount and drift tests | All production tools pass onboarding | Tool Platform Lead | Planned
G5 Experience | S11 | Voice latency, barge-in, avatar state and multi-monitor tests | Integrated experience meets usability baseline | Experience Lead | Planned
G6 Memory | S12 | Admission, provenance, poisoning and deletion evidence | No prohibited/executable poisoned memory | Memory Lead | Planned
G7 Supervised Agent | S14 | UI ambiguity, takeover, workflow draft and end-to-end tests | Supervised actions remain bounded and explainable | Product/Safety | Planned
G8 Security Hardening | S16 | Red-team, privacy, DR and performance reports | No critical finding; thresholds achieved | Security/QA | Planned
G9 Production Readiness | S17 | Pilot results, signed installer, runbooks and dashboards | Go decision recorded by review board | Architecture Board | Planned

## RACI
Deliverable | Accountable | Responsible | Consulted | Informed
Architecture baseline | Lead Architect | Architecture Team | Security, Product, Windows, AI | All workstreams
Policy and immutable restrictions | Security Lead | Security + Windows Engineers | Privacy, Legal/Product | All capability owners
Trusted approval experience | Security Lead | Windows + UX Engineers | Product, Accessibility | Users/pilot
LangGraph and model gateway | AI Lead | AI + Platform Engineers | Security, Privacy, SRE | Product
Windows capability broker | Windows Lead | Windows Engineers | Security, Reliability | AI/Tool teams
Tool Capability Platform | Platform Lead | Tool + Platform Engineers | Security, AI, SRE | Capability owners
Privacy firewall | Privacy Lead | Privacy + Windows Engineers | Security, Product | All data processors
Character and voice | Experience Lead | Godot/3D + Interaction Team | Product, Accessibility, Performance | Users/pilot
Verification and audit | Reliability Lead | Reliability + SRE | Security, Tool, Windows | Architecture Board
Production release | Product Owner | Release + QA + SRE | All leads | Stakeholders/users

## Definition of Done
Category | Required Check | Evidence | Applies To
Code | Reviewed, formatted, static checks clean and maintainability accepted | CI report and review | All engineering stories
Contracts | Versioned schema and compatibility tests updated | Contract test report | APIs/events/tools
Security | Threat impact reviewed; least privilege and denial paths tested | Threat note and security tests | Capabilities/data flows
Privacy | Classification, release, retention and deletion behavior tested | Privacy test evidence | Personal/sensitive data
Policy | Allow/deny/ask and obligations covered | OPA test matrix | Effectful actions
Reliability | Timeout, cancellation, retry, crash and uncertainty paths tested | Failure-injection report | Runtime components
Verification | Independent postcondition predicates implemented | Evidence fixtures | Effectful capabilities
Observability | Trace/metric/log fields added without sensitive content | OTel test/dashboard | Services/workflows
Audit | Security-relevant decisions/effects produce chained events | Audit verification | Policies/actions
UX | States, errors, approval and accessibility are understandable | Usability/accessibility review | User-facing stories
Documentation | ADR/runbook/user docs updated | Published documents | Behavioral/operational change
Demo | Acceptance criterion demonstrated in clean environment | Recorded sprint evidence | All stories